## Cover
PlannerCore™ Lag Auditor
Lag & Lead Audit Report
sample_minimal.xer • Analysed 2026-07-04 17:09
Project ID(s) | 1
Project name(s) | MIN-001
Total tasks | 3
Total relationships | 2
Tool version | 0.1.0
Hours per day used | 8
Analysis timestamp | 2026-07-04 17:09
This report identifies relationship lags and leads as recorded in the analysed XER file. It is a review aid and does not constitute a legal, contractual, or forensic opinion. Reviewers must interpret findings within their own programme context.
THE TRUE TROOP CONSULTING LTD
https://home.thetruetroop.com/

## Executive Summary
Executive Summary
Total relationships parsed | 2
Zero-lag relationships | 2 (100.0%)
Non-zero relationships | 0 (0.0%)
Positive-lag count | 0 (0.0%)
Largest positive lag | 0.0 hrs (0.00 days)
Negative-lead count | 0 (0.0%)
Largest negative lead | -0.0 hrs (-0.00 days)
High-severity count | 0
Critical-severity count | 0
Non-zero rows WITH comments | 0
Non-zero rows WITHOUT comments | 0
Lookup failures (missing pred/succ) | 0
External (cross-project) relationships | 0
DCMA Test 9 (% with lag, target <5%) | 0.0% — PASS
DCMA Test 10 (% with lead, target = 0%) | 0.0% — PASS
Severity distribution
Low | 0
Medium | 0
High | 0
Critical | 0
DCMA 14-Point Schedule Assessment (Defense Contract Management Agency) — Test 9 (Lag) target <5%, Test 10 (Lead) target = 0%. AACE International Recommended Practice 52R-06 — Forensic Schedule Analysis. Society of Construction Law Delay and Disruption Protocol — Position 4.
THE TRUE TROOP CONSULTING LTD • https://home.thetruetroop.com/

## Lag & Lead Detail
Relationship ID | Project ID | Project Name | Predecessor Activity ID | Predecessor Activity Name | Successor Activity ID | Successor Activity Name | Relationship Type | Relationship Type Raw | Lag Hours | Display Lag Days | Classification | Severity | Flags | Relationship Comments | Predecessor WBS Code | Predecessor WBS Name | Predecessor WBS Path | Successor WBS Code | Successor WBS Name | Successor WBS Path | Lookup Status

## Top Issues
Top 10 largest positive lags
Pred ID | Pred Name | Succ ID | Succ Name | Relationship Type | Lag Hours | Lag Days | Severity | Flags
(none)
Top 10 largest negative leads
Pred ID | Pred Name | Succ ID | Succ Name | Relationship Type | Lag Hours | Lag Days | Severity | Flags
(none)
All Critical-severity items
Pred ID | Pred Name | Succ ID | Succ Name | Relationship Type | Lag Hours | Lag Days | Severity | Flags
(none)

## Relationship Type Summary
Counts by Relationship Type × Classification
Relationship Type | Zero Lag | Positive Lag | Negative Lead | Invalid | Row Total
FS | 2 | 0 | 0 | 0 | 2
SS | 0 | 0 | 0 | 0 | 0
FF | 0 | 0 | 0 | 0 | 0
SF | 0 | 0 | 0 | 0 | 0
Unknown | 0 | 0 | 0 | 0 | 0
Column Total | 2 | 0 | 0 | 0 | 2

## WBS Summary
WBS Summary
WBS Code | WBS Name | WBS Path | Non-zero Relationship Count | Average Lag (hours) | Max ¦Lag¦ (hours) | Negative-Lead Count
No non-zero relationships found in any WBS.

## Parser Warnings
Parser Warnings
No parser warnings — XER parsed cleanly.

## Configuration
Run Configuration
Tool version | 0.1.0
Run timestamp | 2026-07-04 17:09
Input file name (no path) | sample_minimal.xer
Hours per day | 8
Positive — Low max (days) | 2
Positive — Medium max (days) | 10
Positive — High max (days) | 20
Negative — Low max (days) | 2
Negative — Medium max (days) | 5
Negative — High max (days) | 10
Include zero-lag rows in detail | No

## ReadMe
What this tool checks
The PlannerCore™ Lag Auditor inspects every relationship record in the analysed XER file and reports those with a non-zero lag or lead. It classifies each as Zero Lag, Positive Lag, Negative Lead or Invalid, and buckets severity using configurable day-based thresholds.
What this tool does NOT check
This release does not recalculate the critical path, does not evaluate missing logic or open ends, does not assess hard or soft constraints, does not compare against a baseline programme, and does not parse resource or cost data.
Methodology citations
DCMA 14-Point Schedule Assessment (Defense Contract Management Agency) — Test 9 (Lag) target <5%, Test 10 (Lead) target = 0%. AACE International Recommended Practice 52R-06 — Forensic Schedule Analysis. Society of Construction Law Delay and Disruption Protocol — Position 4.
Source-of-truth statement
The raw lag_hr_cnt value from the XER is the authoritative lag value. Lag displayed in days throughout this report is a convenience derived from the configurable hours-per-day setting and is labelled accordingly.
Working days vs calendar days
Day values shown here are working days assuming the configured hours-per-day. Calendar-day reconciliation requires the project calendar from P6, which is not parsed in v0.1.
How to interpret severity
Severity is a configurable convenience to aid review triage, not a contractual or legal standard. Adjust thresholds via the command-line flags to match your project's tolerance.
Disclaimer
This report identifies relationship lags and leads as recorded in the analysed XER file. It is a review aid and does not constitute a legal, contractual, or forensic opinion. Reviewers must interpret findings within their own programme context.
Support and home page
THE TRUE TROOP CONSULTING LTD https://home.thetruetroop.com/