## Cover
PlannerCore™ Lag Auditor
Lag & Lead Audit Report
sample_mixed.xer • Analysed 2026-07-04 17:09
Project ID(s) | 1, 2
Project name(s) | MIX-A, MIX-B
Total tasks | 20
Total relationships | 25
Tool version | 0.1.0
Hours per day used | 8
Analysis timestamp | 2026-07-04 17:09
This report identifies relationship lags and leads as recorded in the analysed XER file. It is a review aid and does not constitute a legal, contractual, or forensic opinion. Reviewers must interpret findings within their own programme context.
THE TRUE TROOP CONSULTING LTD
https://home.thetruetroop.com/

## Executive Summary
Executive Summary
Total relationships parsed | 25
Zero-lag relationships | 15 (60.0%)
Non-zero relationships | 10 (40.0%)
Positive-lag count | 7 (28.0%)
Largest positive lag | 240.0 hrs (30.00 days)
Negative-lead count | 3 (12.0%)
Largest negative lead | -40.0 hrs (-5.00 days)
High-severity count | 0
Critical-severity count | 1
Non-zero rows WITH comments | 7
Non-zero rows WITHOUT comments | 3
Lookup failures (missing pred/succ) | 0
External (cross-project) relationships | 1
DCMA Test 9 (% with lag, target <5%) | 28.0% — FAIL
DCMA Test 10 (% with lead, target = 0%) | 12.0% — FAIL
Severity distribution
Low | 5
Medium | 4
High | 0
Critical | 1
DCMA 14-Point Schedule Assessment (Defense Contract Management Agency) — Test 9 (Lag) target <5%, Test 10 (Lead) target = 0%. AACE International Recommended Practice 52R-06 — Forensic Schedule Analysis. Society of Construction Law Delay and Disruption Protocol — Position 4.
THE TRUE TROOP CONSULTING LTD • https://home.thetruetroop.com/

## Lag & Lead Detail
Relationship ID | Project ID | Project Name | Predecessor Activity ID | Predecessor Activity Name | Successor Activity ID | Successor Activity Name | Relationship Type | Relationship Type Raw | Lag Hours | Display Lag Days | Classification | Severity | Flags | Relationship Comments | Predecessor WBS Code | Predecessor WBS Name | Predecessor WBS Path | Successor WBS Code | Successor WBS Name | Successor WBS Path | Lookup Status
5003 | 1 |  | 3003 | Strip-out | 3004 | Structural Strengthening | Start-to-Start (SS) | PR_SS | 16 | 2 | Positive Lag | Low | Non-FS relationship with non-zero lag, Has comments | Strengthening can start 2d after strip-out | 1003 |  |  | 1003 |  |  | OK
5004 | 1 |  | 3004 | Structural Strengthening | 3005 | Pour Slab | Finish-to-Start (FS) | PR_FS | 40 | 5 | Positive Lag | Medium | Has comments | Awaiting compressive test | 1003 |  |  | 1003 |  |  | OK
5005 | 1 |  | 3005 | Pour Slab | 3006 | Brickwork | Finish-to-Start (FS) | PR_FS | 80 | 10 | Positive Lag | Medium | No comments provided |  | 1003 |  |  | 1003 |  |  | OK
5006 | 1 |  | 3006 | Brickwork | 3007 | Roofing | Finish-to-Start (FS) | PR_FS | -16 | -2 | Negative Lead | Low | Negative lead, Has comments | Roofing can start 2d before brick complete | 1003 |  |  | 1003 |  |  | OK
5007 | 1 |  | 3007 | Roofing | 3008 | Glazing | Finish-to-Finish (FF) | PR_FF | 32 | 4 | Positive Lag | Medium | Non-FS relationship with non-zero lag, Has comments | Glazing follows roof finish by 4d | 1003 |  |  | 1003 |  |  | OK
5009 | 1 |  | 3009 | Final Clean | 3010 | Practical Completion | Finish-to-Start (FS) | PR_FS | 240 | 30 | Positive Lag | Critical | Large positive lag, Has comments | 30d hold for client snagging | 1004 |  |  | 1004 |  |  | OK
5011 | 2 |  | 4002 | Design Freeze | 4003 | Utility Diversion | Finish-to-Start (FS) | PR_FS | -40 | -5 | Negative Lead | Medium | Negative lead, No comments provided |  | 2002 |  |  | 2003 |  |  | OK
5014 | 2 |  | 4005 | Site Setup B | 4006 | Piling B | Finish-to-Start (FS) | PR_FS | 8 | 1 | Positive Lag | Low | No comments provided |  | 2004 |  |  | 2004 |  |  | OK
5017 | 2 |  | 4008 | Frame B | 4009 | Envelope B | Start-to-Start (SS) | PR_SS | -8 | -1 | Negative Lead | Low | Negative lead, Non-FS relationship with non-zero lag, Has comments | Envelope can lap with frame | 2004 |  |  | 2004 |  |  | OK
5019 | 2 |  | 4008 | Frame B | 4010 | Fit-out B | Start-to-Finish (SF) | PR_SF | 16 | 2 | Positive Lag | Low | Non-FS relationship with non-zero lag, Start-to-Finish relationship, Has comments | SF tie-in | 2004 |  |  | 2004 |  |  | OK

## Top Issues
Top 10 largest positive lags
Pred ID | Pred Name | Succ ID | Succ Name | Relationship Type | Lag Hours | Lag Days | Severity | Flags
3009 | Final Clean | 3010 | Practical Completion | FS | 240 | 30 | Critical | Large positive lag, Has comments
3005 | Pour Slab | 3006 | Brickwork | FS | 80 | 10 | Medium | No comments provided
3004 | Structural Strengthening | 3005 | Pour Slab | FS | 40 | 5 | Medium | Has comments
3007 | Roofing | 3008 | Glazing | FF | 32 | 4 | Medium | Non-FS relationship with non-zero lag, Has comments
3003 | Strip-out | 3004 | Structural Strengthening | SS | 16 | 2 | Low | Non-FS relationship with non-zero lag, Has comments
4008 | Frame B | 4010 | Fit-out B | SF | 16 | 2 | Low | Non-FS relationship with non-zero lag, Start-to-Finish relationship, Has comments
4005 | Site Setup B | 4006 | Piling B | FS | 8 | 1 | Low | No comments provided
Top 10 largest negative leads
Pred ID | Pred Name | Succ ID | Succ Name | Relationship Type | Lag Hours | Lag Days | Severity | Flags
4002 | Design Freeze | 4003 | Utility Diversion | FS | -40 | -5 | Medium | Negative lead, No comments provided
3006 | Brickwork | 3007 | Roofing | FS | -16 | -2 | Low | Negative lead, Has comments
4008 | Frame B | 4009 | Envelope B | SS | -8 | -1 | Low | Negative lead, Non-FS relationship with non-zero lag, Has comments
All Critical-severity items
Pred ID | Pred Name | Succ ID | Succ Name | Relationship Type | Lag Hours | Lag Days | Severity | Flags
3009 | Final Clean | 3010 | Practical Completion | FS | 240 | 30 | Critical | Large positive lag, Has comments

## Relationship Type Summary
Counts by Relationship Type × Classification
Relationship Type | Zero Lag | Positive Lag | Negative Lead | Invalid | Row Total
FS | 14 | 4 | 2 | 0 | 20
SS | 0 | 1 | 1 | 0 | 2
FF | 0 | 1 | 0 | 0 | 1
SF | 0 | 1 | 0 | 0 | 1
Unknown | 1 | 0 | 0 | 0 | 1
Column Total | 15 | 7 | 3 | 0 | 25

## WBS Summary
WBS Summary
WBS Code | WBS Name | WBS Path | Non-zero Relationship Count | Average Lag (hours) | Max ¦Lag¦ (hours) | Negative-Lead Count
A.C | A — Construction | Project A Root / A — Construction | 10 | 30.4 | 80 | 2
B.C | B — Construction | Project B Root / B — Construction | 6 | 5.33 | 16 | 2
A.H | A — Handover | Project A Root / A — Handover | 2 | 240 | 240 | 0
B.D | B — Design Interface | Project B Root / B — Design Interface | 1 | -40 | 40 | 1
B.E | B — External Interface | Project B Root / B — External Interface | 1 | -40 | 40 | 1

## Parser Warnings
Parser Warnings
Severity | Table | Field | Row Reference | Message
Warning | PROJWBS | parent_wbs_id | 1002 | Cycle detected while walking WBS parents starting at 1002; path reconstruction halted at the cycle entry.
Warning | PROJWBS | parent_wbs_id | 1003 | Cycle detected while walking WBS parents starting at 1003; path reconstruction halted at the cycle entry.
Warning | PROJWBS | parent_wbs_id | 1004 | Cycle detected while walking WBS parents starting at 1004; path reconstruction halted at the cycle entry.
Warning | PROJWBS | parent_wbs_id | 2002 | Cycle detected while walking WBS parents starting at 2002; path reconstruction halted at the cycle entry.
Warning | PROJWBS | parent_wbs_id | 2003 | Cycle detected while walking WBS parents starting at 2003; path reconstruction halted at the cycle entry.
Warning | PROJWBS | parent_wbs_id | 2004 | Cycle detected while walking WBS parents starting at 2004; path reconstruction halted at the cycle entry.

## Configuration
Run Configuration
Tool version | 0.1.0
Run timestamp | 2026-07-04 17:09
Input file name (no path) | sample_mixed.xer
Hours per day | 8
Positive — Low max (days) | 2
Positive — Medium max (days) | 10
Positive — High max (days) | 20
Negative — Low max (days) | 2
Negative — Medium max (days) | 5
Negative — High max (days) | 10
Include zero-lag rows in detail | No

## ReadMe
What this tool checks
The PlannerCore™ Lag Auditor inspects every relationship record in the analysed XER file and reports those with a non-zero lag or lead. It classifies each as Zero Lag, Positive Lag, Negative Lead or Invalid, and buckets severity using configurable day-based thresholds.
What this tool does NOT check
This release does not recalculate the critical path, does not evaluate missing logic or open ends, does not assess hard or soft constraints, does not compare against a baseline programme, and does not parse resource or cost data.
Methodology citations
DCMA 14-Point Schedule Assessment (Defense Contract Management Agency) — Test 9 (Lag) target <5%, Test 10 (Lead) target = 0%. AACE International Recommended Practice 52R-06 — Forensic Schedule Analysis. Society of Construction Law Delay and Disruption Protocol — Position 4.
Source-of-truth statement
The raw lag_hr_cnt value from the XER is the authoritative lag value. Lag displayed in days throughout this report is a convenience derived from the configurable hours-per-day setting and is labelled accordingly.
Working days vs calendar days
Day values shown here are working days assuming the configured hours-per-day. Calendar-day reconciliation requires the project calendar from P6, which is not parsed in v0.1.
How to interpret severity
Severity is a configurable convenience to aid review triage, not a contractual or legal standard. Adjust thresholds via the command-line flags to match your project's tolerance.
Disclaimer
This report identifies relationship lags and leads as recorded in the analysed XER file. It is a review aid and does not constitute a legal, contractual, or forensic opinion. Reviewers must interpret findings within their own programme context.
Support and home page
THE TRUE TROOP CONSULTING LTD https://home.thetruetroop.com/